## Overview (hidden)
Project Name | Priority | ETA | Helper Value | Priority | ETA | Helper Value D | Helper Value P
#VALUE! | #REF! | #REF! | #VALUE! | High | 2024-07-26 | -740 | 28 | -0.037838 | low can be streched to 7 days | low is x | 7x=4y=z | x=4
PSS Longview ISD Multi Purpose Facility | #REF! | #REF! | #REF! | High | 2024-07-25 | -741 | 28 | -0.037787 | medium can be streched to 4 days | medium is y |  | y=7
Al Tahoe/Bayview Well Rehab & Emergency Power | #REF! | #REF! | #REF! | High | 2024-07-30 | -736 | 28 | -0.038043 | high cannot be strected | high is z |  | z=28
Folsom Heights Development Water Booster Pump Station | #REF! | #REF! | #REF! | Medium | 2024-07-22 | -744 | 7 | -0.0094086
Combined Sewer Overflow PS - City of Anacortes | #REF! | #REF! | #REF! | Medium | 2024-07-25 | -741 | 7 | -0.0094467
Umatila Police Station | #REF! | #REF! | #REF! | Medium | 2024-07-30 | -736 | 7 | -0.0095109
West LA-VA Medical Center - New Boiler Plant (Relay Config) | #REF! | #REF! | #REF! | Low | 2024-07-18 | -748 | 4 | -0.0053476
UC Davis Electrical Panel Replacement | #REF! | #REF! | #REF! | Low | 2024-07-25 | -741 | 4 | -0.0053981
City of Lacey - LS 3 Replacement | #REF! | #REF! | #REF! | Low | 2024-07-30 | -736 | 4 | -0.0054348
Island Transit Coupville Base | #REF! | #REF! | #REF!
OCH Catheterization Lab | #REF! | #REF! | #REF!
OCH Catheterization Lab CO#1 | #REF! | #REF! | #REF!
Canadian Solar Dallas | #REF! | #REF! | #REF!
City of Clovis Pump Station E AF Study | #REF! | #REF! | #REF!
Murrieta Childrens Library Expansion Project | #REF! | #REF! | #REF!
Oak Harbor Fire Station # 82 | #REF! | #REF! | #REF!
Brookside Mental Health Rehab Richmond | #REF! | #REF! | #REF!
Catlin Gabel School | #REF! | #REF! | #REF!
Catlin Gabel School CO#1 | #REF! | #REF! | #REF!
Tierra Blanca WWTP | #REF! | #REF! | #REF!
Sapporo Teriyaki | #REF! | #REF! | #REF!
DOW SCO | #REF! | #REF! | #REF!
Canadian Solar Project | #REF! | #REF! | #REF!
Warm Springs Commissary | #REF! | #REF! | #REF!
Steilacoom - Dock Lift Station and Parking Lot Improvement | #REF! | #REF! | #REF!
Richard Bard Elementary School HVAC, Electrical & Fire Alarm | #REF! | #REF! | #REF!
Modesto Library Tenant Improvements | #REF! | #REF! | #REF!
Dom 4 Lift Station MCC and CP Replacement Project | #REF! | #REF! | #REF!
Well 4 Electrical Improvements - City of Auburn | #REF! | #REF! | #REF!
City of Burlingtom - WWTP Influent & Effluent PS Upgrades | #REF! | #REF! | #REF!
Eddyville Fire Station Gear | #REF! | #REF! | #REF!
City of Anacortes - Pump Station 16 | #REF! | #REF! | #REF!
City of Lacey - Lift Station 9 Improvements | #REF! | #REF! | #REF!
City of Lacey - Lift Station 23 Improvements | #REF! | #REF! | #REF!
SH 6 Pump Station Standby Generator | #REF! | #REF! | #REF!
Industrial Wastewater Treatment Facility | #REF! | #REF! | #REF!
Corporate Tenant Improvement - Phase 3 | #REF! | #REF! | #REF!
10MW ALBQ Data Center Neher McGrath Study | #REF! | #REF! | #REF!
Boiler Replacement at John.B Conally Middle School | #REF! | #REF! | #REF!
DELL-PC1 SCCAF Studies | #REF! | #REF! | #REF!
Umatilla Oregon - Power City and Brownell Water & Sewer | #REF! | #REF! | #REF!
Haley Canopy ZEV Infrastructure Improvements Power system Studies | #REF! | #REF! | #REF!
Heatherwood & Heather Gardens PS Rehabilitation | #REF! | #REF! | #REF!
Supplemental Well No 3 Improvements - Watsonville | #REF! | #REF! | #REF!
Eagle and Magnolia Park Electrical Equipment Replacement | #REF! | #REF! | #REF!
Telemark Recycled and Potable Water Booster Pump Station - SCVWA | #REF! | #REF! | #REF!
Optum Madison Center Project | #REF! | #REF! | #REF!
2025 Treatment Plant Improvement - NAPA Sanitation District | #REF! | #REF! | #REF!
SMUCLA MP200 Room B114-35 Nuclear Medicine PET | #REF! | #REF! | #REF!
Oroville WWTP Upgrade | #REF! | #REF! | #REF!
PHX 72 Neher McGrath Study for MV Duct Banks + LV | #REF! | #REF! | #REF!
TxDPS Law Academy & Training Facility Project | #REF! | #REF! | #REF!
Sumner Station | #REF! | #REF! | #REF!
Sumner Station CO#2 | #REF! | #REF! | #REF!
WHARF 2 Generator Site Work-Concord | #REF! | #REF! | #REF!
UCD Campus Outdoor Security | #REF! | #REF! | #REF!
COH - Helford Special Procedure Room | #REF! | #REF! | #REF!
La Verna (Miguel Barroso) | #REF! | #REF! | #REF!
Bayshore, Ravenwood MS, Roseville Galleria Bus Charging & Los Robles | #REF! | #REF! | #REF!
AMD Building D | #REF! | #REF! | #REF!
325 Eastlake | #REF! | #REF! | #REF!
Hot Water Phase 2 - Greenhouses | #REF! | #REF! | #REF!
Old Settlers Park - 3 Sites | #REF! | #REF! | #REF!
Woodbine Development Project | #REF! | #REF! | #REF!
Texas Medical Center (TMC) Transit Center Opportunity | #REF! | #REF! | #REF!
ECY - EV Infrastructure | #REF! | #REF! | #REF!
Arrowhead Regional Medical Center (ARMC) Medical Vacuum System Replacement | #REF! | #REF! | #REF!
Seton Medical Center Austin Electrical Infrastructure CO#1 | #REF! | #REF! | #REF!
Crest Pump Station | #REF! | #REF! | #REF!
Sudden Valley Lift Station 22 | #REF! | #REF! | #REF!
City of Hope - Helford Special Procedure Room CO#1 | #REF! | #REF! | #REF!
Hall of Records | #REF! | #REF! | #REF!
Fairlife Neher McGrath Study | #REF! | #REF! | #REF!
Richmond WWTP Sludge Thickner | #REF! | #REF! | #REF!
CTE Building Modernization - Umatilla | #REF! | #REF! | #REF!
Grayson College - Residence Hall | #REF! | #REF! | #REF!
Country Place PFAS Treatment - lake Wood Water Disrtict | #REF! | #REF! | #REF!
Vancouver Affordable Housing | #REF! | #REF! | #REF!
Seton Medical Center Austin Electrical Infrastructure | #REF! | #REF! | #REF!
RHCA Headquarters Renovation | #REF! | #REF! | #REF!
SMUCLA Phase 2 | #REF! | #REF! | #REF!
Issaquah Transportation Bus Charging | #REF! | #REF! | #REF!
PR Distribution Project | #REF! | #REF! | #REF!
Yermo School's New Gym | #REF! | #REF! | #REF!
Judy Water Treatment Plant W1 pump station replacement | #REF! | #REF! | #REF!
Zone 3 Booster Pump Improvements - City of Cle Elum | #REF! | #REF! | #REF!
PR Distribution Project Model Conversion ETAP TO SKM CO#1 | #REF! | #REF! | #REF!
EED Schick Shadel | #REF! | #REF! | #REF!
DNR Electrical Upgrades -Meridian | #REF! | #REF! | #REF!
O'Neill Building West Wing, Lab 18 & Lab 19 | #REF! | #REF! | #REF!
Marin County Veterans Memorial Auditorium Building Systems Upgrade | #REF! | #REF! | #REF!
PR Distribution Project CO#2 | #REF! | #REF! | #REF!
AMD Building D CO#3 | #REF! | #REF! | #REF!
Snubber Nucor Gallatin Facility | #REF! | #REF! | #REF!
Reedly College AF Study | #REF! | #REF! | #REF!
EED Schick Schadel SCCAF Study CO#1 | #REF! | #REF! | #REF!
Hutto South WWTP Influent Lift Station | #REF! | #REF! | #REF!
UCD Segundo Dinning Commons | #REF! | #REF! | #REF!
IAD192 | #REF! | #REF! | #REF!
PR Distribution Project CO#3 | #REF! | #REF! | #REF!
AMD Building D CO#4 | #REF! | #REF! | #REF!
Battery Electric Bus Charging Infrastructure Phase 1 - El Monte Station (Div. 9) | #REF! | #REF! | #REF!
High Island ISD Construction of New K-12th School & Gym | #REF! | #REF! | #REF!
Makr Furniture Project | #REF! | #REF! | #REF!
Project LAYLA | #REF! | #REF! | #REF!
Multicare Endoscopy Center - Yakima | #REF! | #REF! | #REF!
Elder - Turquoise Units | #REF! | #REF! | #REF!
LIGO - CEBEX Laboratory | #REF! | #REF! | #REF!
City of Palo Alto - UCC Generator Replacement | #REF! | #REF! | #REF!
Amazon Warehouse - ABQ1 OBD-A | #REF! | #REF! | #REF!
Entegris Project | #REF! | #REF! | #REF!
Skywalker Phase 3.4A | #REF! | #REF! | #REF!
West Coast Grocery Co - IRGRA | #REF! | #REF! | #REF!
Old Port 1 Lift Station - City of Olympia | #REF! | #REF! | #REF!
Domiguez Water Pump Coordination Study | #REF! | #REF! | #REF!
Snubber Nucor Gallatin Facility CO#1 | #REF! | #REF! | #REF!
Irvine Valley College - Arts Promenade and Coffee Structure | #REF! | #REF! | #REF!
Moccasin WTFS Project | #REF! | #REF! | #REF!
Zones Auburn | #REF! | #REF! | #REF!
Country Place PFAS Treatment Project CO#1 - Lakewood Water District | #REF! | #REF! | #REF!
NMSU Computer Center | #REF! | #REF! | #REF!
Arnold WWTF Phase I Improvements Project | #REF! | #REF! | #REF!
UCD Segundo Dining Commons CO#1 | #REF! | #REF! | #REF!
Wesco Generator | #REF! | #REF! | #REF!
Sewage Pump Station Improvement - North Tahoe PUD | #REF! | #REF! | #REF!
Smithson Valley HS Interior Renovation - Comal I.S.D | #REF! | #REF! | #REF!
Cart Wash Replacement - CCRMC | #REF! | #REF! | #REF!
TJJD Evins Generator Improvements - ERJC | #REF! | #REF! | #REF!
Skywalker Complete Facility | #REF! | #REF! | #REF!
White Oaks Elementary School HVAC Upgrades - San Carlos | #REF! | #REF! | #REF!
Fujimi CMP2 | #REF! | #REF! | #REF!
Maintenance Facilities - City of Issaquah | #REF! | #REF! | #REF!
John Muir ES New TKK - AUSD | #REF! | #REF! | #REF!
West Portal Elementary School Modernization Phase 2 | #REF! | #REF! | #REF!
Fire Station 52 - Comal County ESD 3 | #REF! | #REF! | #REF!
Oak Harbor Storage CTE Building | #REF! | #REF! | #REF!
Rainier HS Main Service Switchboard Replacement | #REF! | #REF! | #REF!
EED Schick Schadel SCCAF Study CO#2 | #REF! | #REF! | #REF!
Walnut Grove Elementary School TK Building - PUSD | #REF! | #REF! | #REF!
PSS DWS5 Phase 1E - Everett, WA | #REF! | #REF! | #REF!
New Electrical Service at HESD Central Kitchen | #REF! | #REF! | #REF!
Canadian Solar Project CO#1 | #REF! | #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
Formulas:
Helper Value D = IF([ETA]-TODAY()=0,1,[ETA]-TODAY())

## Utilization
|  |  | May Wk1 | May Wk2 | May Wk3 | May Wk4 | May Wk5 | Jun Wk1 | Jun Wk2 | Jun Wk3 | Jun Wk4 | Jun Wk5 | Jul Wk1 | Jul Wk2 | Jul Wk3 | Jul Wk4 | Jul Wk5 | Aug Wk1 | Aug Wk2 | Aug Wk3 | Aug Wk4 | Aug Wk5 | Sept Wk1 | Sept Wk2 | Sept Wk3 | Sept Wk4 | Oct Wk1 | Oct Wk2 | Oct Wk3 | Oct Wk4 | Oct Wk5 | Nov Wk1 | Nov Wk2 | Nov Wk3 | Nov Wk4 | Dec Wk1 | Dec Wk2 | Dec Wk3 | Dec Wk4
|  |  | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-01 | 2026-08-08 | 2026-08-15 | 2026-08-22 | 2026-08-29 | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26
zain.abideen | RMS24002 | Richard Bard Elementary School HVAC, Electrical & Fire Alarm | 2026-05-29: 40; 2026-06-01: 40; 2026-06-29: 40; 2026-07-29: 40; 2026-08-29: 40
zain.abideen | ATS25006 | RHCA Headquarters Renovation | bar: 2026-06-01 to 2026-09-26
zain.abideen | SBE25009 | Hot Water Phase 2 - Greenhouses | bar: 2026-06-01 to 2026-09-26
zain.abideen | NC25001 | CTE Building Modernization - Umatilla | bar: 2026-06-01 to 2026-09-26
zain.abideen | PRE25003 | 325 Eastlake | bar: 2026-06-01 to 2026-09-26
zain.abideen | CESC25003 | Catlin Gabel School | bar: 2026-05-01; 2026-06-01 to 2026-09-26
zain.abideen | ATS25009 | Seton Medical Center Austin Electrical Infrastructure | bar: 2026-05-01; 2026-06-01 to 2026-09-26
zain.abideen | CESC25005 | Warm Springs Commissary | bar: 2026-05-01; 2026-06-01 to 2026-09-26
zain.abideen | CEI25002 | WHARF 2 Generator Site Work-Concord | bar: 2026-05-01; 2026-06-01 to 2026-09-26
zain.abideen | EPS25007 | Hall of Records | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
zain.abideen | EPS25008 | Reedly College AF Study | bar: 2026-05-01; 2026-06-01 to 2026-09-26
zain.abideen | ATS25011 | Boiler Replacement at John.B Conally Middle School | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
zain.abideen | NE26004 | Marin County Veterans Memorial Auditorium Building Systems Upgrade | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
zain.abideen | ATS26015 | TxDPS Law Academy & Training Facility Project | bar: 2026-06-01 to 2026-09-26
zain.abideen | GPS26005 | Elder - Turquoise Units | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
zain.abideen | ATS26017 | Smithson Valley HS Interior Renovation - Comal I.S.D | bar: 2026-06-01 to 2026-09-26
zain.abideen | PRE26006 | Skywalker Complete Facility | bar: 2026-06-01 to 2026-09-26
zain.abideen | GPS22001 | La Verna (Miguel Barroso) | 2026-05-22: 19; 2026-06-22: 19; 2026-07-22: 19; 2026-08-22: 19; 2026-09-26: 19
zain.abideen | CESC25004 | Vancouver Affordable Housing | bar: 2026-05-01 to 2026-05-15
[7 empty] | 40 | 40 |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
m.sulaiman | PBS25005 | COH - Helford Special Procedure Room | bar: 2026-06-01 to 2026-09-26
m.sulaiman | CE25001 | ECY - EV Infrastructure | bar: 2026-06-01 to 2026-09-26
m.sulaiman | AET25001 | Issaquah Transportation Bus Charging | bar: 2026-06-01 to 2026-09-26
m.sulaiman | AG25001 | Yermo School's New Gym | bar: 2026-06-01 to 2026-09-26
m.sulaiman | SECO25001 | City of Burlingtom - WWTP Influent & Effluent PS Upgrades | bar: 2026-05-01; 2026-06-01 to 2026-09-26
m.sulaiman | SBE25010 | UCD Campus Outdoor Security | bar: 2026-05-01; 2026-06-01 to 2026-09-26
m.sulaiman | BVE25002 | Al Tahoe/Bayview Well Rehab & Emergency Power | bar: 2026-05-01; 2026-06-01 to 2026-09-26
m.sulaiman | BVE25003 | UC Davis Electrical Panel Replacement | bar: 2026-05-01; 2026-06-01 to 2026-09-26
m.sulaiman | PBS25005.1 | City of Hope - Helford Special Procedure Room CO#1 | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
m.sulaiman | MESC25002 | PR Distribution Project | bar: 2026-05-01; 2026-06-01 to 2026-09-26
m.sulaiman | BDE25004 | PSS Longview ISD Multi Purpose Facility | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
m.sulaiman | MESC25002.1 | PR Distribution Project Model Conversion ETAP TO SKM CO#1 | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
m.sulaiman | MESC25002.3 | PR Distribution Project CO#3 | bar: 2026-06-01 to 2026-09-26
m.sulaiman | ERE26001 | Fire Station 52 - Comal County ESD 3 | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
m.sulaiman | MESC25001 | Texas Medical Center (TMC) Transit Center Opportunity | bar: 2026-06-01 to 2026-09-26
irsa.sarfaraz | FES25001 | Crest Pump Station | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | CPE25004 | OCH Catheterization Lab | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | CJFE25001 | Modesto Library Tenant Improvements | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | ME25001 | City of Anacortes - Pump Station 16 | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | CESC25001 | Eddyville Fire Station Gear | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | BE25001 | SH 6 Pump Station Standby Generator | bar: 2026-05-01; 2026-06-01 to 2026-08-15
irsa.sarfaraz | SCCE24001.1 | Bayshore, Ravenwood MS, Roseville Galleria Bus Charging & Los Robles | bar: 2026-05-01; 2026-06-01 to 2026-08-15
irsa.sarfaraz | CPE25004.1 | OCH Catheterization Lab CO#1 | bar: 2026-05-01; 2026-06-01 to 2026-08-15
irsa.sarfaraz | CSEC25001 | Industrial Wastewater Treatment Facility | bar: 2026-05-01; 2026-06-01 to 2026-08-15
irsa.sarfaraz | CDI25001 | Canadian Solar Project | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
irsa.sarfaraz | AE25001 | Judy Water Treatment Plant W1 pump station replacement | bar: 2026-05-01; 2026-06-01 to 2026-08-15; 2026-09-05
irsa.sarfaraz | NUE25001 | DNR Electrical Upgrades -Meridian | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
irsa.sarfaraz | HE25003.1 | EED Schick Schadel SCCAF Study CO#1 | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
irsa.sarfaraz | CDI25001.1 | Canadian Solar Project CO#1 | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | APB26001 | Island Transit Coupville Base | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
irsa.sarfaraz | MBE26005 | Dom 4 Lift Station MCC and CP Replacement Project | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | SEC26002 | Corporate Tenant Improvement - Phase 3 | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | SEC26003 | O'Neill Building West Wing, Lab 18 & Lab 19 | 2026-05-22: 19; 2026-06-22: 19; 2026-07-22: 19; 2026-08-22: 19; 2026-09-26: 19
irsa.sarfaraz | CPE25004.2 | OCH Catheterization Lab CO#2 | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | SCCE26005 | City of Palo Alto - UCC Generator Replacement
irsa.sarfaraz | PRE26004 | Skywalker Phase 3.4A
irsa.sarfaraz | APB26004 | Oak Harbor Storage CTE Building | bar: 2026-06-01 to 2026-08-15
irsa.sarfaraz | HE26003.2 | EED Schick Schadel SCCAF Study CO#2 | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | PCLIS24001 | PHX 72 Neher McGrath Study for MV Duct Banks + LV | bar: 2026-05-29 to 2026-08-15
Wareesha Azwar | HBH24003 | DOW SCO | bar: 2026-05-29 to 2026-08-15
Wareesha Azwar | OEI25001 | Sapporo Teriyaki | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | TKE25001 | Tierra Blanca WWTP | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | BIE25001 | Oroville WWTP Upgrade | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | JEC25001 | Woodbine Development Project | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
Wareesha Azwar | SEC25001 | Sumner Station | bar: 2026-05-01; 2026-06-01 to 2026-08-15; 2026-09-05
Wareesha Azwar | ATS25007 | Old Settlers Park - 3 Sites | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
Wareesha Azwar | ATS25008 | AMD Building D | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
Wareesha Azwar | OEMA25001 | Fairlife Neher McGrath Study | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | PDI25001 | 10MW ALBQ Data Center Neher McGrath Study | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
Wareesha Azwar | ATS25012 | DELL-PC1 SCCAF Studies | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | ATS25008.4 | AMD Building D CO#4 | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | GWE25001.1 | Snubber Nucor Gallatin Facility CO#1 | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | GPS26006 | Domiguez Water Pump Coordination Study | bar: 2026-06-01 to 2026-08-15
Wareesha Azwar | SJE26001 | Sewage Pump Station Improvement - North Tahoe PUD | 2026-05-22: 19; 2026-06-22: 19; 2026-07-22: 19; 2026-08-22: 19; 2026-09-26: 19
Wareesha Azwar | SEC25001.1 | Sumner Station CO#2 | bar: 2026-06-01 to 2026-08-15
mustafa.abdullah | MBE24002 | Richmond WWTP Sludge Thickner | bar: 2026-05-15; 2026-06-01 to 2026-08-15
mustafa.abdullah | VEG25003 | Country Place PFAS Treatment - lake Wood Water Disrtict | 2026-05-29: 12
mustafa.abdullah | BDE25003 | Grayson College - Residence Hall | bar: 2026-06-01 to 2026-08-15
mustafa.abdullah | SMEP25001 | Haley Canopy ZEV Infrastructure Improvements Power system Studies | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
mustafa.abdullah | FEI25005 | Folsom Heights Development Water Booster Pump Station | bar: 2026-05-01; 2026-06-01 to 2026-08-15; 2026-09-05
mustafa.abdullah | DE25002 | Well 4 Electrical Improvements - City of Auburn | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
mustafa.abdullah | CEC25002 | Zone 3 Booster Pump Improvements - City of Cle Elum | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
mustafa.abdullah | CSEC26002 | Heatherwood & Heather Gardens PS Rehabilitation | bar: 2026-06-01 to 2026-08-15
mustafa.abdullah | CVE26001 | Supplemental Well No 3 Improvements - Watsonville | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
mustafa.abdullah | CDI26002 | Canadian Solar Dallas | bar: 2026-06-01 to 2026-08-15
mustafa.abdullah | SIS26001 | Project LAYLA | bar: 2026-06-01 to 2026-08-15
mustafa.abdullah | VEG25003.1 | Country Place PFAS Treatment Project CO#1 - Lakewood Water District | 2026-05-22: 19; 2026-06-22: 19; 2026-07-22: 19; 2026-08-22: 19; 2026-09-26: 19
zahir.hussain | BES25003 | City of Lacey - Lift Station 23 Improvements | bar: 2026-05-15; 2026-06-01 to 2026-08-15
zahir.hussain | NC25004 | Umatilla Oregon - Power City and Brownell Water & Sewer | bar: 2026-05-15; 2026-06-01 to 2026-08-15
zahir.hussain | BES25004 | Steilacoom - Dock Lift Station and Parking Lot Improvement | bar: 2026-05-15; 2026-06-01 to 2026-08-15
zahir.hussain | SECO26002 | Combined Sewer Overflow PS - City of Anacortes | bar: 2026-05-15; 2026-06-01 to 2026-08-15
zahir.hussain | APB26002 | Sudden Valley Lift Station 22 | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
zahir.hussain | CEDTC26001 | Umatila Police Station | bar: 2026-05-01; 2026-06-01 to 2026-08-15; 2026-09-05
zahir.hussain | CLE26001 | Battery Electric Bus Charging Infrastructure Phase 1 - El Monte Station (Div. 9) | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
zahir.hussain | CEDTC26002 | Multicare Endoscopy Center - Yakima | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
zahir.hussain | SEC26005 | Amazon Warehouse - ABQ1 OBD-A | bar: 2026-06-01 to 2026-08-15
zahir.hussain | CJFE26002 | Arnold WWTF Phase I Improvements Project | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
zahir.hussain | RPL26001 | NMSU Computer Center | bar: 2026-06-01 to 2026-08-15
zahir.hussain | CESC26006 | Fujimi CMP2 | bar: 2026-06-01 to 2026-08-15
zahir.hussain | MBE26008 | West Portal Elementary School Modernization Phase 2 | 2026-05-22: 19; 2026-06-22: 19; 2026-07-22: 19; 2026-08-22: 19; 2026-09-26: 19
zahir.hussain | SEC26006 | PSS DWS5 Phase 1E - Everett, WA | 2026-05-22: 38; 2026-06-22: 38; 2026-07-22: 38; 2026-08-22: 38; 2026-09-26: 38
zahir.hussain | SM26001 | New Electrical Service at HESD Central Kitchen
Areeb | AIOE26001 | Telemark Recycled and Potable Water Booster Pump Station - SCVWA | bar: 2026-05-15; 2026-06-01 to 2026-08-15
Areeb | MBE26006 | 2025 Treatment Plant Improvement - NAPA Sanitation District | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
Areeb | DOE26001 | Murrieta Childrens Library Expansion Project | bar: 2026-05-01; 2026-06-01 to 2026-08-15; 2026-09-05
Areeb | APB26003 | Oak Harbor Fire Station # 82 | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
Areeb | HE26003 | Makr Furniture Project | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
Areeb | STE26001 | Entegris Project | bar: 2026-06-01 to 2026-08-15
Areeb | GPS26007 | Irvine Valley College - Arts Promenade and Coffee Structure | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
Areeb | SBE26007.1 | UCD Segundo Dining Commons CO#1 | bar: 2026-06-01 to 2026-08-15
Areeb | PRE26007 | Maintenance Facilities - City of Issaquah | bar: 2026-06-01 to 2026-08-15
Areeb | SCCE26006 | John Muir ES New TKK - AUSD | 2026-05-22: 19; 2026-06-22: 19; 2026-07-22: 19; 2026-08-22: 19; 2026-09-26: 19
Areeb | BES26005 | Rainier HS Main Service Switchboard Replacement | 2026-05-22: 38; 2026-06-22: 38; 2026-07-22: 38; 2026-08-22: 38; 2026-09-26: 38
nawab.naveed | VEG25002 | City of Lacey - LS 3 Replacement | bar: 2026-05-29 to 2026-08-15
nawab.naveed | EPS25009 | City of Clovis Pump Station E AF Study | bar: 2026-05-29 to 2026-08-15
nawab.naveed | CME26001 | Eagle and Magnolia Park Electrical Equipment Replacement | bar: 2026-05-29 to 2026-08-15
nawab.naveed | SEC26004 | Optum Madison Center Project | bar: 2026-05-29 to 2026-08-15
nawab.naveed | MBE26007 | Brookside Mental Health Rehab Richmond | 2026-05-01: 40; 2026-06-01: 40; 2026-07-01: 40; 2026-08-01: 40; 2026-09-05: 40
nawab.naveed | APE26001 | High Island ISD Construction of New K-12th School & Gym | bar: 2026-05-01; 2026-06-01 to 2026-08-15; 2026-09-05
nawab.naveed | NC26005 | LIGO - CEBEX Laboratory | 2026-05-08: 5; 2026-06-08: 5; 2026-07-08: 5; 2026-08-08: 5; 2026-09-12: 5
nawab.naveed | PRE26005 | West Coast Grocery Co - IRGRA | 2026-05-08: 35; 2026-05-15: 19; 2026-06-08: 35; 2026-06-15: 19; 2026-07-08: 35; 2026-07-15: 19; 2026-08-08: 35; 2026-08-15: 19; 2026-09-12: 35; 2026-09-19: 19
nawab.naveed | FEI26006 | Moccasin WTFS Project | bar: 2026-06-01 to 2026-08-15
nawab.naveed | ATS26016 | Wesco Generator | 2026-05-15: 21; 2026-05-22: 19; 2026-06-15: 21; 2026-06-22: 19; 2026-07-15: 21; 2026-07-22: 19; 2026-08-15: 21; 2026-08-22: 19; 2026-09-19: 21; 2026-09-26: 19
nawab.naveed | BEI26001 | Cart Wash Replacement - CCRMC | bar: 2026-06-01 to 2026-08-15
nawab.naveed | CECI26001 | White Oaks Elementary School HVAC Upgrades - San Carlos | bar: 2026-06-01 to 2026-08-15
nawab.naveed | SCCE26007 | Walnut Grove Elementary School TK Building - PUSD | 2026-05-22: 19; 2026-06-22: 19; 2026-07-22: 19; 2026-08-22: 19; 2026-09-26: 19